## Slide 1: In-Process Review (IPR) Guidance
To help standardize and improve the effectiveness of IPRs, the Office of the Assistant Secretary of Defense for Acquisition (ASD(A)) developed this attached IPR briefing template for program offices and ASD(A) subject matter experts to use as a “best practices” guide for IPR briefings. Components and the relevant Deputy Assistant Secretary of Defense should brief other topics they determine warrant Defense Acquisition Executive attention.
Please contact Mr. David Cadman with questions at: david.s.cadman.civ@mail.mil.
Do Not Brief This Slide

## Slide 2
[Program Name] IPR Briefing for DASD or USD(A&S)
ADD DATE
DRAFT – PRE DECISIONAL

## Slide 3: [Program Name] IPR Briefing for DASD or USD(A&S)
[Month, Day, Year]
[PEO/PO Lead Briefer Name]
As necessary, change to Service Symbol in Slide Master
PEO / PM Brief
DRAFT – PRE DECISIONAL
Use of existing Program Charts is Encouraged

## Slide 4: Agenda
Purpose
Program Overview
PEO/PM Top Concerns
Requirements Overview - KPPs
IMS / Schedule
APB
Hardware Status
Software / Integration Efforts / Status
Technical Risks
Export / International Considerations (if applicable)
Status of Legacy Program(s) Being Replaced (if applicable)
Program Funding
DASD / ASD(A) Comments
PEO / PM Comments
Actions Items
Backups
PEO / PM Brief
“20 Chart Limit”
Not including the Cover chart, Purpose chart, Agenda chart, or Backups

## Slide 5: Purpose
Clearly state the reason for this meeting
  (e.g. Annual IPR for Information or guidance or decision or etc.)
Top level status of program
  (Provide top level health of the program. E.g. On plan, delayed but recoverable, delayed, need help, etc.)
Desired outcome of this meeting
  (Complete the annual requirement, receive guidance, request review of requirements, etc.)
  (Decisions needed)
Program continues to execute efforts and funding aligned with xxx
PEO / PM Brief
This should be a one bullet BLUF: e.g. PEO/PM assessment if the Program is on track or different.

## Slide 6: [Program Name] Program Overview
  Provide a narrative mission description
  Provide acquisition phase
  Provide prime contractor names and contract type for each
  Provide program-specific graphics if available
Example
PEO / PM Brief
Use of existing Program Charts is Encouraged

## Slide 7: PEO / PM Top Concerns
Use this slide to discuss the most critical issues facing the program from the PEO/PM perspective

## Slide 8: Requirements Overview
REQUIREMENT | THRESHOLD (T) / OBJECTIVE (O) | Previous IPR Estimate MMYYYY | Previous IPR Estimate MMYYYY | PM Current Estimate MMYYYY
KPP 1 Force Protection | XXXXX (T) XXXXX (T=O) XXXXX(T=O) XXXXX(T) |  |  | 
KPP 2 System Survivability | XXXXX (T) XXXXX (T=O) XXXXX (T=O) |  |  | 
KPP 3 Sustainment | XXXXX 95% threshold (T), 99% (O) XXXXX greater than 90% (T=O) Reliability – % probability of operating at least XX hrs mission without incurring a system abort (T=O) |  |  | 
KPP 4 Energy |  |  |  | 
KPP 5 Integrated Defense Effectiveness | XXXXX (TF) (T=O) XXXXX (T=O) XXXXX Tt=O) |  |  | 
KPP 6 Common AMD Mission Command | XXXXX (T=O) XXXXX (T=O) XXXXX (T=O) |  |  | 
KPP 7 Net Ready / Joint Interoperability | XXXXX (T) XXXXX (T=O) |  |  | 
Clearly indicate If Threshold and Objective
Use Red/Yellow/Green to indicate if on track to meet the requirement
PEO / PM Brief
Show 2 Previous IPRs
Example
CDD Validated by JROC: DD MMM YYYY

## Slide 9: IMS / Schedule
2023 |  |  |  |  |  |  |  |  |  |  |  | 2024 |  |  |  |  |  |  |  |  |  |  |  | 2025 |  |  |  |  |  |  |  |  |  |  | 
JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Radar
Reentry Vehicle
Support Eq
C2
DT
IOT&E
IOC
Rocket Motor
MS A
MS C
xxx
MS B
Work Projection ---- xxxx
xxx
FOC
Operational
Milestones
LUT
Example
Time Now
Tests
Version# and Date
NOTE: Use current PEO/PM IMS / Schedule
???
Clearly show Time Now
PEO / PM Brief
For current and future major milestone/events for which estimated dates have changed over the past two IPRs, indicate in gray the biggest delta of the prior two IPR dates compared to current estimate. Make the icon red if the current estimate is later than previous; make the icon green if the current estimate is earlier than previous.
If the PMO has a different way to display these trends over time, please work with the relevant A&S Portfolio Manager to discuss alternate formats.
IOT&E Quick Look Findings
Legend | 
ACRONYM LIST | 
Red icon if event is estimated to occur later than prev 2 IPRs
Green icon if event is estimated to occur earlier than prev 2 IPRs
Black icon if no change to event estimate since prev 2 IPRs
DT – May24 est
IOT&E – May24 est

## Slide 10: Acquisition Program Baseline (APB)
+6 mos
Baseline
Baseline
Baseline
Baseline
Cost
  PAUC
  - APUC
Schedule
  IOC or FOC
  Next Major Event
Major Concerns / Issues
PEO / PM insight into existing or known potential concerns or issues that has not already been covered in previous charts.
If no additional concerns / issues, then indicate “None”
+10%
+15%
Y
G
G
R
Example
PEO / PM Brief
Notes: Purpose:
This chart displays a program’s essential performance elements in the context of the system’s cost, schedule and technical risks. This information:
  Provides the JROC an understanding of desired capabilities balanced against the technical risks and costs of a system prior to validating the capability documents (CDD or CPD). Therefore, the primary focus of the cost driver and technology quads is their relationship to the system KPPs.
  Allows the JROC to assess, over time, the impact of desired system performance parameters on the ability to deliver the system within the Acquisition Program Baseline (APB) Cost and Schedule.
Over time, as the program transitions through its acquisition lifecycle, performance attributes will progress towards the threshold KPP/KSA values and, corresponding technology risk will be reduced as reflected in higher TRLs. Additionally, the major cost drivers and program costs will also change over time as the program goes from one phase to the next and may shift away from the cost of the KPPs especially after Critical Design Reviews and first article testing.
The Program Manager is the best source of data for this chart. Starting in FY07, all ACAT I Program Managers are required to report this information as part of the new USD(AT&L) DAES monthly report.

## Slide 11: Hardware Status
Hardware efforts
  Delayed [Discussion should include impact mitigation efforts]
  % complete
  Other as determined by Service
Knowledge Points Status
  Development or Design [Example: Events that could identify integration problems or HW maturity problems causing potential schedule delay and / or increased cost]
  Test Results
  Other as determined by Service
Hardware Path on Schedule and within Projected Funding
Pictures, graphs, schedules are good
PEO / PM Brief

## Slide 12: Software / Integration Efforts /Status
Major SW efforts
  Delayed [Discussion should include impact mitigation efforts]
  % complete
  Other as determined by Service
Knowledge Points Status
  Development or Design [Example: Events that could identify potential integration problems between HW / SW]
  Integration Concerns / Issues
  Test Results
  Other as determined by Service
Software / Integration Path on Schedule and within Projected Funding
PEO / PM Brief
Pictures, graphs, schedules are good

## Slide 13: Technical Risks [e.g. development, test, integration, etc.]
IF the system failure modes identified in the IOT&E Operational Evaluation Report (OER) are not corrected, THEN the system will be assessed as ineffective at FOT&E
MITIGATION:
Action 1 (Complete 25-XXX-XX)
Action 2 (Complete 08-XXX-XX)
Action 3 (Planned 12-XXX-XX)
Action 4 (Planned 02-XXX-XX)
RISK 1.
System Effectiveness
4Q FYXX
RISK 2.
NET Safety Release and Training Package
1Q FYXX
IF Major End Items are not delivered on schedule THEN the selected COA for involvement in IFTC XX is delayed, impacting the first two fieldlings and execution.
MITIGATION:
Action 1 (Complete 25-XXX-XX)
Action 2 (Complete 08-XXX-XX)
Action 3 (Planned 12-XXX-XX)
Action 4 (Planned 02-XXX-XX)
RISK 3
Initial LRIP Deliveries
3Q FYXX
2
1
3
Current Assessment
Risk Originated at IOTE
IF safety release and Training Package are not available by 20XX THEN New Equipment Training (NET) will be delayed and directly impact other program milestones to include FOT&E, LRIP material release and unit fielding. unit fielding.
MITIGATION:
Action 1 (Complete 25-XXX-XX)
Action 2 (Complete 08-XXX-XX)
Action 3 (Planned 12-XXX-XX)
Action 4 (Planned 02-XXX-XX)
Example
PEO / PM Brief

## Slide 14: Production and Sustainment Risks
XXXX
MITIGATION:
XXXXXX
RISK 1.
XXXXXX
4Q FY24
RISK 2.
XXXXX
1Q FY25
XXXX
MITIGATION:
XXXXXX
RISK 3
XXXXXX
3Q FY24
2
1
3
Current Assessment
Risk Originated at IOTE
XXXX
MITIGATION:
XXXXXX
Example
PEO / PM Brief

## Slide 15: Export / International Considerations
Use this slide to discuss all export / international considerations
XXXXX
PEO / PM Brief

## Slide 16: Status of Legacy Program(s) being replaced
E.g., if this system is replacing a legacy system(s), and the schedule for FOC of this system is sliding, what sustainment actions/investments will be required to keep the legacy system(s) operational for longer than originally planned?
Construction of this slide may require the PM’s coordination with another PMO/PEO
Pictures, graphs, schedules are good
XXXXX
PEO / PM Brief
Include this chart if applicable

## Slide 17: Program Funding & Quantities
Program Funding & Quantities |  | Acquisition to O&S Cost Ratio |  |  |  |  |  | (BY yyyy) | Curr Est | D Current | D Original
 |  | Total Req'd Acq (BYXX$M): |  |  |  | $ | % | PAUC: |  |  | 
 |  | Total Req'd O&S (BYXX$M): |  |  |  | $ | % | APUC: |  |  | 
($ in Millions / Then Year) | Prior | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY24-28 | To Comp | Prog Total
RDT&E | Primary Line Items: |  |  |  |  |  |  |  |  |  | 
Prior $ (PB 23) |  |  |  |  |  |  |  |  |  |  | 
Current $ (POM 24) |  |  |  |  |  |  |  |  |  |  | 
Delta $ (Current - Prior) |  |  |  |  |  |  |  |  |  |  | 
Required1 $ |  |  |  |  |  |  |  |  |  |  | 
Delta $ (Current - Required) |  |  |  |  |  |  |  |  |  |  | 
PROCUREMENT | Primary Line Items: |  |  |  |  |  |  |  |  |  | 
Prior $ (PB 23) |  |  |  |  |  |  |  |  |  |  | 
Current $ (POM 24) |  |  |  |  |  |  |  |  |  |  | 
Delta $ (Current - Prior) |  |  |  |  |  |  |  |  |  |  | 
Required1 $ |  |  |  |  |  |  |  |  |  |  | 
Delta $ (Current - Required) |  |  |  |  |  |  |  |  |  |  | 
MILCON | Primary Line Items: |  |  |  |  |  |  |  |  |  | 
Prior $ (PB 23) |  |  |  |  |  |  |  |  |  |  | 
Current $ (POM 24) |  |  |  |  |  |  |  |  |  |  | 
Delta $ (Current - Prior) |  |  |  |  |  |  |  |  |  |  | 
Required1 $ |  |  |  |  |  |  |  |  |  |  | 
Delta $ (Current - Required) |  |  |  |  |  |  |  |  |  |  | 
SYSTEM O&M2 | Primary Line Items: |  |  |  |  |  |  |  |  |  | 
Prior $ (PB 23) |  |  |  |  |  |  |  |  |  |  | 
Current $ (POM 24) |  |  |  |  |  |  |  |  |  |  | 
Delta $ (Current - Prior) |  |  |  |  |  |  |  |  |  |  | 
Required1 $ |  |  |  |  |  |  |  |  |  |  | 
Delta $ (Current - Required) |  |  |  |  |  |  |  |  |  |  | 
TOTAL |  |  |  |  |  |  |  |  |  |  | 
Prior $ (PB 23) |  |  |  |  |  |  |  |  |  |  | 
Current $ (POM 24) |  |  |  |  |  |  |  |  |  |  | 
Delta $ (Current - Prior) |  |  |  |  |  |  |  |  |  |  | 
Required1 $ |  |  |  |  |  |  |  |  |  |  | 
Delta $ (Current - Required) |  |  |  |  |  |  |  |  |  |  | 
QUANTITIES |  |  |  |  |  |  |  |  |  |  | 
Prior Qty (PB 23) |  |  |  |  |  |  |  |  |  |  | 
Current Qty (POM 24) |  |  |  |  |  |  |  |  |  |  | 
Delta Qty (Current - Prior) |  |  |  |  |  |  |  |  |  |  | 
Required1 Qty |  |  |  |  |  |  |  |  |  |  | 
Delta Qty (Current - Required) |  |  |  |  |  |  |  |  |  |  | 
Note 1. Requirement Source: [e.g., OSD CAPE ICE, July 2017] |  |  |  |  |  |  |  |  |  |  | 
Use Current PEO/PM Spruill Chart
PEO / PM Brief
Add previous two IPR Spruill charts in backup
Notes: Notes:
Fill in values in the unshaded (white) cells only. The rest of the data is calculated automatically. The spreadsheet cells will round to the nearest hundred thousand dollars ($0.1M).
Display investment funding for baselined acquisition program only (not O&S or follow-on investment).
Delete any appropriation sections that have no budgeted or required costs.
Programs must use footnotes to state source of "Required" estimate, O&M service life projection & cost categories, and any RDT&E-funded quantities (if any).
Program offices are to use the latest version of the funding program template. Regularly check the DAB Calendar as the IPT Program Funding template changes as PPBES events occur.
Definitions:
Prior: President’s Budget (PB) position submitted prior to the Current budget position. Although the President only submits the FYDP to Congress, the cells for the next fiscal year and “To-Complete” should be populated for the investment appropriations using the values reported in the Selected Acquisition Report or latest DAES associated with that PB (if available).
Current: Latest approved Service POM budget position or approved President’s Budget.
  Use POM Position from August through January; Use PB from February through July.
  When the DoD Appropriation is enacted, programs should update that cell of all the "Current” PB funding and quantity rows to reflect the actual appropriated amounts.
Required: Latest estimate of funds required to successfully execute program, i.e., support the Warfighter and not simply match available budget TOAs. Typically, this would reflect the Will Cost estimate, Service Cost Position (SCP), or PEO-supported Program Office Estimate (POE) that has not yet been validated by Service Cost Agency or CAPE. Note: total required quantity is the acquisition objective recognized by the Joint Staff or similar body and would be reflected in the program's Acquisition Program Baseline (APB) or similar document but may not be reflected in the budget due to affordability or funding issues.
System O&M: In this section, list the O&M-funded costs from initial system deployment through end of system operations. Include all costs of operating, maintaining, and supporting a fielded system. Specifically, this consists of the costs (organic and contractor) of equipment, supplies, software, and services associated with operating, modifying, maintaining, supplying, training, and supporting a system in the DoD inventory. Do not include acquisition-related O&M, and non-O&M O&S costs such as military personnel and investment-funded system improvements. Also, do not include disposal costs, which represent a separate phase of the program life cycle. Please address questions on the O&M requirements to OSD(AT&L)/L&MR...see POC below.
Total Required Acquisition (BY$M): Current Estimate of Total RDT&E, procurement, MILCON and acquisition-related O&M in base-year dollars as reported in the program’s quarterly DAES (if applicable). The percentage displayed is the portion of the Acquisition cost out of the sum of Acquisition and O&S costs.
Total Required O&S (BY$M): Current Estimate of Total Operating and Support costs in base-year dollars as reported in the program’s quarterly DAES (if applicable). A foot note should identify the projected service life. The percentage displayed is the portion of the O&S cost out of the sum of Acquisition and O&S costs
Curr Est (APUC): Program Manager’s current estimate of Average Procurement Unit Cost, in base-year dollars (total procurement divided by procurement-funded quantities). The APUC should match the values reported in the program's quarterly DAES (if applicable). (The current estimate is the latest PB with fact of life changes).
Curr Est (PAUC): Program Manager’s current estimate of Program Acquisition Unit Cost, in base-year dollars (total RDT&E, procurement, MILCON and acquisition-related O&M divided by total quantity). The PAUC should match the values reported in the program's quarterly DAES (if applicable).
Points of Contact:
Army Programs: Mr. Vance Hinch, OSD(AT&L)/ARA vance.l.hinch.ctr@mail.mil 703-697-5384
Navy Programs: CDR Dave Zielinski, OSD(AT&L)/ARA E-mail: david.m.zielinski.mil@mail.mil
Phone: 703-697-8020
Air Force Programs: Lt Col Thomas Shrum, OSD(AT&L)/ARA E-mail: thomas.c.shrum.mil@mail.mil Phone: 703-614-2805
O&M Section: Jim Kelly, OSD(AT&L)/LM&R E-mail: james.l.kelly.civ@mail.mil Phone: 703-693-5716

## Slide 18: DASD / ASD Comments
Upcoming Decision Events:
    Decision Event 1 (Date)
    Decision Event 2 (Date)
    Decision Event 3 (Date)
Other Key Points for USD(A&S) Discussion:
    Key Point 1 [Consider any connection to DAES RPT]
    Key Point 2 [Consider long standing unsolved actions]
    Key Point 3
Concerns:
    XXX
Review of action(s) assigned, specifying OPRs and ECDs, from this meeting
DASD - Brief

## Slide 19: PEO / PM Comments / Conclusion
Guidance / Decision requested from USD(A&S):
    Guidance Requested
    Guidance Requested
    Decision Requested
Support requested from USD(A&S) / OSD:
    Key Point 1
    Key Point 2
    Key Point 3
PEO / PM Brief

## Slide 20: Outstanding Action(s) from Prior IPRs
No. | Issue Description | Remarks / Status | OPR / POC: Name / Email | Start / Due Date
1 |  |  | Jane Doe jane.d.doe.civ@mail.mil | 12-02-24 / 02-03-25
2 |  |  |  | 
3 |  |  |  | 
4 |  |  |  | 
5 |  |  |  | 
6 |  |  |  | 
7 |  |  |  | 
Move Closed Action Items to backup chart
PEO / PM Brief

## Slide 21: Backup

## Slide 22: Backup
Parking Lot
  Topics that arise during the IPR that require either more discussion time or more data than what is available during the IPR
    Could result in follow-on focused meetings
    Could result in specific topic added for next IPR
    Could become action item
    Etc.
Include IMS / Schedule charts from previous 2 IPRs
  Looking for trends
Include two previous IPR Spruill Charts
Include Action Item chart of Closed actions from previous IPR
Include Service backups as needed
Backup Charts are FYI. And not intended to be briefed.

## Slide 23: Parking Lot
Issues that require additional time or additional data to address a particular question will be moved to the “Parking Lot” chart. This will allow the meeting to stay on track.
List questions that were not answered during IPR.
This chart will be developed during the IPR MTG.
Parking Lot issues might require follow-up focused meetings or turn into an action item.

## Slide 24: Closed Action(s) Previous IPR(s)
No. | Issue Description | Remarks / Status | OPR / POC: Name / Email | Start / Due Date
1 |  |  | Jane Doe jane.d.doe.civ@mail.mil | 12-02-24 / 02-03-25
2 |  |  |  | 
3 |  |  |  | 
4 |  |  |  | 
5 |  |  |  | 
6 |  |  |  | 
7 |  |  |  | 

## Slide 25
[Program Name] IPR Briefing for USD(A&S)
ADD DATE